## WBS V1
| Phases | Description | Est.
1 | Project Management
1.1 | Requirement Gathering | Meeting the client and gathering all relevant information | 8
1.2 | Analysis and Scope Definition | Analysing the the gathered requirements and defining the scope of the project | 4
1.3 | QA Standards Definition | Defining the acceptance criteria and standards for quality | 2
1.4 | Review | Revision of the all requirements if necessary | 2
2 | Design
2.1 | Architecture Design | Selecting the stack and designing the architecture of the system/app | 2
2.2 | Database Design | Creating the design and schema of the database | 3
2.3 | UI Design | designing the UI of the pages and creating wireframes of the prototype | 12
17
3 | Development
3.1 | Weight Tracking | This module deals with all operations related to Weight
3.1.1 | Front-end
3.1.1.1 | Weight Logger | Conversion of components design into html. These components will be used on Dashboard, Goal Page, and Profile Page | 2
3.1.1.2 | Weight Progress Graph | Conversion of graphs design into html. This components will be used on Dashboard, and Goal Page
3.1.2 | Back-end
3.1.2.1 | Weight Logging | Methods to log weight and properly store in the Database | 4
3.1.2.2 | Weight Progress | Methods to track weight progress based on different filters: weekly, monthly, annually, Goal wise etc. and display them in a graph.
6
3.2 | Food Tracking | This module deals with all operations related to Food
3.2.1 | Front-end
3.2.1.1 | Food Logger | Conversion of the food intake logger design into html markups. This component will be used on Food Page, and Dashboard | 2
3.2.1.2 | Food History | Conversion of Food history page and it's respective components into html markups.
3.2.2 | Back-end |  | 4
3.2.2.1 | Food API integration | Integration of external food API for search and calories information.
3.2.2.2 | Food logging | Methods to log food to the Database properly.
3.3 | Exercise Tracking | This module deals with all operations related to Exercise
3.3.1 | Front-end |  | 2
3.3.1.1 | Exercise Logging | Conversion of the Exercise logger design into html markups. This component will be used on Exercise Page, and Dashboard
3.3.1.2 | Exercise History | Conversion of Exercise history page and its respective components into html markups.
3.3.2 | Back-end |  | 4
3.3.2.1 | Exercise API integration | Integration of external Exercise API for search and calories information.
3.3.2.2 | Exercise logging | Methods to log weight to the Database properly.
6
3.4 | User Details | Conversion of the exercise logger design into html markups. This component will be used on Exercise Page, and Dashboard
3.4.1 | Front-end
3.4.1.1 | User Profile | Conversion of the User Profile design into html markups. | 2
| login and Signup | Conversion of the login and signup designs into html markups.
3.4.2 | Back-end |  | 6
3.4.2.1 | User Profile | Methods to create and track updates from user profile and fetch user information from Database.
3.4.2.2 | Login and Signup | Methods to facilitate the process of Login and signup.
8
3.5 | Goals | This module deals with all operations related to Goals
3.5.1 | Front-end |  | 2
3.5.1.1 | Goal Summary | Conversion of the goals summary card design into html markups. This component will be used on Goal Page, and Dashboard
3.5.1.2 | Goal Card | Conversion of design of goal card, shows a single goal, into html markups.
3.5.2 | Back-end |  | 2
3.5.2.1 | Goal | Methods to create, retrieve, update and deleted from the Database properly.
4
3.6 | Recipes | This module deals with all operations related to Recipes
3.6.1 | Front-end |  | 3
3.6.1.1 | Recipes creation | Conversion of the Recipe logger design into html markups. This component will be used on Recipe Page, and Dashboard
3.6.1.2 | Recipe Listing | Conversion of Recipe Listing page and it's respective components into html markups.
3.6.2 | Back-end |  | 3
3.6.2.1 | Recipe fetching | Methods to track to fetch, update, delete from Database.
6
3.7 | Landing Page
3.7.1 | Front-end |  | 3
3.7.1 | Landing Page | Conversion of the Landing Page and its respective components into html markups.
3.7.2 | Back-end |  | 3
3.7.2.1 | Contact | Method to take contact information of the user from Contact Us form and send an auto generated email to the admin
3.7.2.1 | Testimonials | Method to take retrieve testimonials from the database
6
3.8 | Dashboard
3.8.1 | front-end |  | 3
3.8.1.1 | Notification | conversion of all notification components' design into html markups.
3.8.2 | Back-end |  | 3
| notification | fetch data from Database,and display notification
6
5 | QA Standards Definition
| Test Cases Preparation | Creation of test cases to test all components. | 2
| Test Case Execution | Execution of all test cases | 2
| Bug Fixing | Fixing all bugs discovered in test cases | 6
10

## features
Features | Sub-Features | Priority
Login and Signup |  | High
Landing Page |  | Intermediate
Header
Footer
Testimonials
Contact
Home Page |  | High
Weight Logger
Today's Summary
Intake Logger
Progress Graph
| Exercise Logger | Intermediate
| Notifications | low
User Profile |  | High
User Details
Food Page |  | High
Food History Table
Exercise Page |  | Intermediate
Exercise History Table
Goal Page |  | High
Goal Listing
Current Goal Summary
Goal Details Page |  | High
Goal Details
Food Details Page |  | Low
Food Details
Recipe Page |  | Low
Recipes Listing
Recipe Details Page |  | Low
Challenges |  | Low

## WBS V2
| Phases | Description | Est.
1 | Project Management
1.1 | Requirement Gathering | Meeting the client and gathering all relevant information | 8
1.2 | Analysis and Scope Definition | Analysing the the gathered requirements and defining the scope of the project | 4
1.3 | QA Standards Definition | Defining the acceptance criteria and standards for quality | 2
1.4 | Review | Revision of the all requirements if necessary | 2
2 | Design
2.1 | Architecture Design
| System Architecture Diagram |  | 1
| Components Break Down |  | 1
2.2 | Database Design | Creating the design and schema of the database
| ERD |  | 3
2.3 | UI Design | Designing the UI of the pages and creating wireframes of the prototype
| Wireframes |  | 2
| Pages designs |  | 10
2.4 | Class Diagram |  | 1
Environment Setup
| Repository Initialization |  | 1
| IDE and Libraries/Frameworks setup |  | 1
3 | Development
Landing Page
| Landing Page | Front-end: Conversion of design into HTML | 3
| Contact | Back-end: Method to take contact information of the user from Contact Us form and send an auto generated email to the admin | 1.5
| Testimonials | Back-end: Method to take retrieve testimonials from the database | 0.5
| Login and Signup | Frontend: Conversion of their respective font-end design into HTML | 2
|  | Backend: Get Data from client, perform validations | 3
Home Page
| weight logger | Front-end : Conversion of design in to HTML | 1
|  | Back-end: Get data from client and save it into Database. | 1
| Current Goal Summary | Front-end : Conversion of design in to HTML | 1
|  | Back-end: retrieve info about today intake from Database | 1.5
| Intake logger | Front-end: Conversion of design into HTML | 1
|  | Back-end : get data from client and save into Database | 3
| Goal progress Graph | Front-end : Conversion of design in to HTML | 1.5
|  | Back-end : Retrieve progress from Database based on filters, and convert it into required format so that can be shown in graph | 1
| Exercise logging | Front-end : Conversion of design in to HTML | 1.5
|  | Back-end: get data from client and save into Database. | 3
| Notification | Front-end : Conversion of design in to HTML | 1
|  | Back-end: Fetch data from Database, and display notifications- | 1
| User Profile | Front-end : Conversion of design in to HTML | 2
|  | Back-end: Get data from client, perform CRUD and respective validation on profile data. | 2
Food Page
| Food History table | Front-end : Conversion of design in to HTML | 1
|  | Back-end: Retrieve data from database | 3
Exercise Page
| Exercise History Table | Front-end : Conversion of design in to HTML | 1
|  | back-end: Retrieve data from database | 3
Goal Page
| Current goal Details | Front-end : Conversion of design in to HTML | 1.5
|  | Back-end: Retrieve current goal's details from Database | 3
| All goal history | Front-end : Conversion of design in to HTML | 1.5
|  | Back-end: retrieve previous goals | 3
| Goal Editing | Front-end: convert into HTML | 1
|  | Back-end: retrieve current goal's details from Database and save updates | 2
| Recipe Page | front-end: convert into HTML design, and show detail of the page ,and fetch from server | 1
|  | Back-end: Retrive Recipes based on its ID | 2
| Goal Details Page | Front-end : Conversion of design in to HTML | 1.5
|  | Back-end: Retrieve goals based on ID | 3
| Food Details Page | Front-end : Conversion of design in to HTML | 1.5
|  | Back-end: Retrieve foods based on its ID | 3
| Recipe Details Page | front-end: convert into HTML design, and show detail of the Recipe,and fetch from server | 1.5
|  | Back-end: Retrive Recipes based on its ID | 1
5 | QA Standards Definition
| Test Cases Preparation | Creation of test cases to test all components. | 8
| Test Case Execution | Execution of all test cases | 2
| Bug Fixing | Fixing all bugs discovered in test cases | 21

## Estimates
Features | Project Management | Design | Development | QA | Bug Fixing | Total
Login and Signup | 1 | 2 | 6 | 2 | 2 | 13
Landing Page | 0.5 | 1 | 5 | 0.5 | 1 | 8
Home Page | 2 | 3 | 17.5 | 4 | 3 | 29.5
User Profile | 1 | 1 | 4 | 2 | 1 | 9
Food Page | 1 | 1 | 4 | 1 | 2 | 9
Exercise Page | 1 | 1 | 4 | 1 | 2 | 9
Goal Page | 2 | 3 | 12 | 2 | 3 | 22
Goal Details Page | 1 | 1 | 5 | 1 | 2 | 10
Food Details Page | 1 | 1 | 5 | 1 | 2 | 10
Recipe Page | 1 | 2 | 3 | 1 | 1 | 8
Recipe Details Page | 1 | 2 | 4.5 | 1 | 2 | 10.5
Total | 12.5 | 18 | 70 | 16.5 | 21 | 138